## Data
People & Task Data
Person | Team | Activity | Category | Owner | Start Date | End Date | % Done
Bruce Wayne | TEAM 1 | Act 001 | Design | Barbara Gordon | 2023-07-01 | 2023-07-08 | 59%
James Gordon | TEAM 1 | Act 002 | Deployment | Harley Quinn | 2023-07-01 | 2023-07-11 | 70%
Alfred Pennyworth | TEAM 1 | Act 003 | Requirements | Richard Grayson | 2023-07-07 | 2023-07-07 | 62%
Bane | TEAM 1 | Act 004 | Requirements | Selina Kyle | 2023-07-08 | 2023-07-18 | 60%
Selina Kyle | TEAM 1 | Act 005 | Design | Richard Grayson | 2023-07-09 | 2023-07-12 | 75%
Harley Quinn | TEAM 2 | Act 006 | Design | Bruce Wayne | 2023-07-10 | 2023-07-16 | 100%
Barbara Gordon | TEAM 2 | Act 007 | Development | Barbara Gordon | 2023-07-07 | 2023-07-19 | 78%
Richard Grayson | TEAM 2 | Act 008 | Testing | Barbara Gordon | 2023-07-07 | 2023-07-16 | 61%
Joker | TEAM 2 | Act 009 | Requirements | Alfred Pennyworth | 2023-07-07 | 2023-07-11 | 100%
Lucius Fox | TEAM 2 | Act 010 | Requirements | Alfred Pennyworth | 2023-07-08 | 2023-07-17 | 27%
|  | Act 011 | Development | Selina Kyle | 2023-07-08 | 2023-07-18 | 100%
|  | Act 012 | Deployment | Joker | 2023-07-08 | 2023-07-18 | 88%
|  | Act 013 | Design | Lucius Fox | 2023-07-09 | 2023-07-17 | 51%
|  | Act 014 | Requirements | Harley Quinn | 2023-07-11 | 2023-07-19 | 95%
|  | Act 015 | Testing | Bane | 2023-07-17 | 2023-07-27 | 70%
|  | Act 016 | Deployment | Selina Kyle | 2023-07-17 | 2023-07-19 | 99%
|  | Act 017 | Development | Barbara Gordon | 2023-07-19 | 2023-07-19 | 100%
|  | Act 018 | Requirements | Harley Quinn | 2023-07-16 | 2023-07-22 | 100%
|  | Act 019 | Deployment | Joker | 2023-07-17 | 2023-07-22 | 100%
|  | Act 020 | Requirements | Alfred Pennyworth | 2023-07-18 | 2023-07-28 | 83%
|  | Act 021 | Development | Alfred Pennyworth | 2023-07-18 | 2023-07-27 | 100%
|  | Act 022 | Deployment | Harley Quinn | 2023-07-18 | 2023-07-21 | 44%
|  | Act 023 | Development | James Gordon | 2023-07-19 | 2023-07-26 | 100%
|  | Act 024 | Testing | Lucius Fox | 2023-07-19 | 2023-07-28 | 88%
|  | Act 025 | Deployment | James Gordon | 2023-07-21 | 2023-07-29 | 100%
|  | Act 026 | Testing | Selina Kyle | 2023-07-27 | 2023-07-30 | 70%
|  | Act 027 | Deployment | James Gordon | 2023-07-28 | 2023-07-28 | 100%
|  | Act 028 | Deployment | Bane | 2023-07-28 | 2023-08-02 | 79%
|  | Act 029 | Testing | Bruce Wayne | 2023-07-29 | 2023-07-31 | 100%
|  | Act 030 | Testing | Richard Grayson | 2023-07-27 | 2023-08-08 | 100%
|  | Act 031 | Development | Bane | 2023-07-27 | 2023-08-10 | 76%
|  | Act 032 | Deployment | Joker | 2023-07-29 | 2023-08-02 | 22%
|  | Act 033 | Testing | Alfred Pennyworth | 2023-07-29 | 2023-08-08 | 67%
|  | Act 034 | Requirements | Selina Kyle | 2023-07-29 | 2023-08-10 | 100%
|  | Act 035 | Requirements | James Gordon | 2023-07-29 | 2023-08-10 | 100%
|  | Act 036 | Development | Bane | 2023-07-30 | 2023-08-07 | 100%
|  | Act 037 | Requirements | Richard Grayson | 2023-08-01 | 2023-08-08 | 100%
|  | Act 038 | Deployment | Bane | 2023-08-02 | 2023-08-09 | 100%
|  | Act 039 | Design | Lucius Fox | 2023-08-07 | 2023-08-09 | 100%
|  | Act 040 | Requirements | Lucius Fox | 2023-08-07 | 2023-08-11 | 27%
|  | Act 041 | Design | Richard Grayson | 2023-08-07 | 2023-08-10 | 100%
|  | Act 042 | Testing | James Gordon | 2023-08-07 | 2023-08-09 | 100%
|  | Act 043 | Requirements | Barbara Gordon | 2023-08-09 | 2023-08-11 | 84%
|  | Act 044 | Deployment | Richard Grayson | 2023-08-07 | 2023-08-19 | 45%
|  | Act 045 | Development | Bruce Wayne | 2023-08-08 | 2023-08-18 | 92%
|  | Act 046 | Testing | Bane | 2023-08-09 | 2023-08-19 | 66%
|  | Act 047 | Design | James Gordon | 2023-08-10 | 2023-08-17 | 65%
|  | Act 048 | Requirements | Bruce Wayne | 2023-08-11 | 2023-08-19 | 100%
|  | Act 049 | Deployment | Barbara Gordon | 2023-08-17 | 2023-08-19 | 79%
|  | Act 050 | Design | Joker | 2023-08-18 | 2023-08-27 | 100%
|  | Act 051 | Testing | Alfred Pennyworth | 2023-08-19 | 2023-08-22 | 96%
|  | Act 052 | Design | Bruce Wayne | 2023-08-17 | 2023-08-27 | 100%
|  | Act 053 | Design | Lucius Fox | 2023-08-19 | 2023-08-28 | 59%
|  | Act 054 | Development | Barbara Gordon | 2023-08-21 | 2023-08-27 | 100%
|  | Act 055 | Testing | Barbara Gordon | 2023-08-27 | 2023-08-26 | 21%
|  | Act 056 | Requirements | Joker | 2023-08-29 | 2023-08-29 | 96%
|  | Act 057 | Design | Alfred Pennyworth | 2023-08-29 | 2023-09-08 | 62%
|  | Act 058 | Development | Selina Kyle | 2023-08-29 | 2023-09-01 | 72%
|  | Act 059 | Development | Harley Quinn | 2023-08-29 | 2023-09-01 | 45%
|  | Act 060 | Deployment | Richard Grayson | 2023-08-26 | 2023-09-10 | 25%
|  | Act 061 | Requirements | James Gordon | 2023-08-28 | 2023-09-07 | 87%
|  | Act 062 | Design | Bane | 2023-08-30 | 2023-09-08 | 100%
|  | Act 063 | Development | Lucius Fox | 2023-08-30 | 2023-09-07 | 0%
|  | Act 064 | Design | Lucius Fox | 2023-09-01 | 2023-09-09 | 0%
|  | Act 065 | Development | Alfred Pennyworth | 2023-09-01 | 2023-09-08 | 0%
|  | Act 066 | Testing | Richard Grayson | 2023-09-02 | 2023-09-10 | 0%
|  | Act 067 | Requirements | Barbara Gordon | 2023-09-02 | 2023-09-10 | 0%
|  | Act 068 | Deployment | Joker | 2023-09-08 | 2023-09-17 | 0%
|  | Act 069 | Deployment | Joker | 2023-09-09 | 2023-09-12 | 0%
|  | Act 070 | Development | James Gordon | 2023-09-09 | 2023-09-08 | 0%
|  | Act 071 | Design | Bruce Wayne | 2023-09-07 | 2023-09-12 | 0%
|  | Act 072 | Requirements | Richard Grayson | 2023-09-07 | 2023-09-17 | 0%
|  | Act 073 | Testing | Selina Kyle | 2023-09-09 | 2023-09-17 | 0%
|  | Act 074 | Design | Bane | 2023-09-10 | 2023-09-20 | 0%
|  | Act 075 | Deployment | Selina Kyle | 2023-09-11 | 2023-09-18 | 0%
|  | Act 076 | Deployment | Barbara Gordon | 2023-09-12 | 2023-09-19 | 0%
|  | Act 077 | Design | Richard Grayson | 2023-09-17 | 2023-09-20 | 0%
|  | Act 078 | Requirements | Selina Kyle | 2023-09-17 | 2023-09-22 | 0%
|  | Act 079 | Deployment | Barbara Gordon | 2023-09-18 | 2023-09-19 | 0%
|  | Act 080 | Testing | Barbara Gordon | 2023-09-19 | 2023-09-21 | 0%
|  | Act 081 | Design | Harley Quinn | 2023-09-16 | 2023-09-26 | 0%
|  | Act 082 | Design | Richard Grayson | 2023-09-16 | 2023-09-20 | 0%
|  | Act 083 | Development | Barbara Gordon | 2023-09-17 | 2023-09-29 | 0%
|  | Act 084 | Requirements | Alfred Pennyworth | 2023-09-18 | 2023-09-26 | 0%
|  | Act 085 | Development | James Gordon | 2023-09-18 | 2023-09-27 | 0%
|  | Act 086 | Development | Richard Grayson | 2023-09-19 | 2023-09-27 | 0%
|  | Act 087 | Requirements | Bane | 2023-09-20 | 2023-09-28 | 0%
|  | Act 088 | Deployment | Bane | 2023-09-22 | 2023-09-26 | 0%
|  | Act 089 | Testing | Lucius Fox | 2023-09-27 | 2023-09-26 | 0%
|  | Act 090 | Requirements | Barbara Gordon | 2023-09-27 | 2023-09-28 | 0%
|  | Act 091 | Design | Joker | 2023-09-29 | 2023-09-28 | 0%
|  | Act 092 | Requirements | Bane | 2023-09-27 | 2023-10-09 | 0%
|  | Act 093 | Requirements | James Gordon | 2023-09-29 | 2023-10-02 | 0%
|  | Act 094 | Requirements | Lucius Fox | 2023-09-30 | 2023-10-07 | 0%
|  | Act 095 | Requirements | Selina Kyle | 2023-09-16 | 2023-10-08 | 0%
|  | Act 096 | Deployment | Barbara Gordon | 2023-10-01 | 2023-10-08 | 0%
|  | Act 097 | Design | Lucius Fox | 2023-10-01 | 2023-10-08 | 0%
|  | Act 098 | Testing | Lucius Fox | 2023-10-01 | 2023-10-09 | 0%
|  | Act 099 | Design | Barbara Gordon | 2023-10-07 | 2023-10-10 | 0%
|  | Act 100 | Requirements | James Gordon | 2023-10-09 | 2023-10-09 | 0%

## calculation
Category | Activity | Min of Start Date | Max of End Date | start date | 2023-08-17
Deployment |  | 2023-07-17 | 2023-09-26
| Act 016 | 2023-07-17 | 2023-07-19
| Act 025 | 2023-07-21 | 2023-07-29
| Act 027 | 2023-07-28 | 2023-07-28
| Act 028 | 2023-07-28 | 2023-08-02
| Act 038 | 2023-08-02 | 2023-08-09
| Act 075 | 2023-09-11 | 2023-09-18
| Act 088 | 2023-09-22 | 2023-09-26
Design |  | 2023-07-10 | 2023-09-20
| Act 006 | 2023-07-10 | 2023-07-16
| Act 047 | 2023-08-10 | 2023-08-17
| Act 052 | 2023-08-17 | 2023-08-27
| Act 057 | 2023-08-29 | 2023-09-08
| Act 062 | 2023-08-30 | 2023-09-08
| Act 071 | 2023-09-07 | 2023-09-12
| Act 074 | 2023-09-10 | 2023-09-20
Development |  | 2023-07-08 | 2023-09-27
| Act 011 | 2023-07-08 | 2023-07-18
| Act 021 | 2023-07-18 | 2023-07-27
| Act 023 | 2023-07-19 | 2023-07-26
| Act 031 | 2023-07-27 | 2023-08-10
| Act 036 | 2023-07-30 | 2023-08-07
| Act 045 | 2023-08-08 | 2023-08-18
| Act 058 | 2023-08-29 | 2023-09-01
| Act 065 | 2023-09-01 | 2023-09-08
| Act 070 | 2023-09-09 | 2023-09-08
| Act 085 | 2023-09-18 | 2023-09-27
Requirements |  | 2023-07-07 | 2023-10-09
| Act 004 | 2023-07-08 | 2023-07-18
| Act 009 | 2023-07-07 | 2023-07-11
| Act 010 | 2023-07-08 | 2023-07-17
| Act 020 | 2023-07-18 | 2023-07-28
| Act 034 | 2023-07-29 | 2023-08-10
| Act 035 | 2023-07-29 | 2023-08-10
| Act 048 | 2023-08-11 | 2023-08-19
| Act 061 | 2023-08-28 | 2023-09-07
| Act 078 | 2023-09-17 | 2023-09-22
| Act 084 | 2023-09-18 | 2023-09-26
| Act 087 | 2023-09-20 | 2023-09-28
| Act 092 | 2023-09-27 | 2023-10-09
| Act 093 | 2023-09-29 | 2023-10-02
| Act 095 | 2023-09-16 | 2023-10-08
| Act 100 | 2023-10-09 | 2023-10-09
Testing |  | 2023-07-17 | 2023-09-17
| Act 015 | 2023-07-17 | 2023-07-27
| Act 026 | 2023-07-27 | 2023-07-30
| Act 029 | 2023-07-29 | 2023-07-31
| Act 033 | 2023-07-29 | 2023-08-08
| Act 042 | 2023-08-07 | 2023-08-09
| Act 046 | 2023-08-09 | 2023-08-19
| Act 051 | 2023-08-19 | 2023-08-22
| Act 073 | 2023-09-09 | 2023-09-17
Grand Total |  | 2023-07-07 | 2023-10-09

## GantT chart
 | time axis 2023-08-17 to 2023-10-15
 | time axis 2023-08-17 to 2023-10-15
 | time axis 2023-08-08 to 2023-10-06
Category | Activity | Person | Start | End | % | CMPLT | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr | fltr
Deployment |  |  | 2023-07-17 | 2023-09-26 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 016 | Selina Kyle | 2023-07-17 | 2023-07-19 | 99% | 0.99 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 025 | James Gordon | 2023-07-21 | 2023-07-29 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 027 | James Gordon | 2023-07-28 | 2023-07-28 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 028 | Bane | 2023-07-28 | 2023-08-02 | 79% | 0.79 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 038 | Bane | 2023-08-02 | 2023-08-09 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 075 | Selina Kyle | 2023-09-11 | 2023-09-18 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 088 | Bane | 2023-09-22 | 2023-09-26 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Design |  |  | 2023-07-10 | 2023-09-20 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 006 | Bruce Wayne | 2023-07-10 | 2023-07-16 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 047 | James Gordon | 2023-08-10 | 2023-08-17 | 65% | 0.65 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 052 | Bruce Wayne | 2023-08-17 | 2023-08-27 | 100% | 1 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 057 | Alfred Pennyworth | 2023-08-29 | 2023-09-08 | 62% | 0.62 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 062 | Bane | 2023-08-30 | 2023-09-08 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 071 | Bruce Wayne | 2023-09-07 | 2023-09-12 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 074 | Bane | 2023-09-10 | 2023-09-20 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Development |  |  | 2023-07-08 | 2023-09-27 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 011 | Selina Kyle | 2023-07-08 | 2023-07-18 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 021 | Alfred Pennyworth | 2023-07-18 | 2023-07-27 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 023 | James Gordon | 2023-07-19 | 2023-07-26 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 031 | Bane | 2023-07-27 | 2023-08-10 | 76% | 0.76 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 036 | Bane | 2023-07-30 | 2023-08-07 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 045 | Bruce Wayne | 2023-08-08 | 2023-08-18 | 92% | 0.92 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 058 | Selina Kyle | 2023-08-29 | 2023-09-01 | 72% | 0.72 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 065 | Alfred Pennyworth | 2023-09-01 | 2023-09-08 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 070 | James Gordon | 2023-09-09 | 2023-09-08 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 085 | James Gordon | 2023-09-18 | 2023-09-27 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Requirements |  |  | 2023-07-07 | 2023-10-09 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 004 | Selina Kyle | 2023-07-08 | 2023-07-18 | 60% | 0.6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 009 | Alfred Pennyworth | 2023-07-07 | 2023-07-11 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 010 | Alfred Pennyworth | 2023-07-08 | 2023-07-17 | 27% | 0.27 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 020 | Alfred Pennyworth | 2023-07-18 | 2023-07-28 | 83% | 0.83 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 034 | Selina Kyle | 2023-07-29 | 2023-08-10 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 035 | James Gordon | 2023-07-29 | 2023-08-10 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 048 | Bruce Wayne | 2023-08-11 | 2023-08-19 | 100% | 1 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 061 | James Gordon | 2023-08-28 | 2023-09-07 | 87% | 0.87 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 078 | Selina Kyle | 2023-09-17 | 2023-09-22 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 084 | Alfred Pennyworth | 2023-09-18 | 2023-09-26 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 087 | Bane | 2023-09-20 | 2023-09-28 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 092 | Bane | 2023-09-27 | 2023-10-09 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 093 | James Gordon | 2023-09-29 | 2023-10-02 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 095 | Selina Kyle | 2023-09-16 | 2023-10-08 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 100 | James Gordon | 2023-10-09 | 2023-10-09 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Testing |  |  | 2023-07-17 | 2023-09-17 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 015 | Bane | 2023-07-17 | 2023-07-27 | 70% | 0.7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 026 | Selina Kyle | 2023-07-27 | 2023-07-30 | 70% | 0.7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 029 | Bruce Wayne | 2023-07-29 | 2023-07-31 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 033 | Alfred Pennyworth | 2023-07-29 | 2023-08-08 | 67% | 0.67 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 042 | James Gordon | 2023-08-07 | 2023-08-09 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 046 | Bane | 2023-08-09 | 2023-08-19 | 66% | 0.66 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 051 | Alfred Pennyworth | 2023-08-19 | 2023-08-22 | 96% | 0.96 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 073 | Selina Kyle | 2023-09-09 | 2023-09-17 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Grand Total | [6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.